## Guide
APD Project Tracker
A single-file, OneDrive/SharePoint-hosted version of the APD Project Management Dashboard (without the AI features).
Getting started
1. Add a project | Go to Projects and type the project name in the first empty row (column A). Everything else on that row is optional; grey columns calculate themselves.
2. Log records | On any register sheet, pick the Project from the dropdown in column A and fill in the row. Dropdowns, date and number checks are built in.
3. View results | Dashboard shows the portfolio, alerts and upcoming work. Project Summary (pick a project in C3) is a printable one-page report. Gantt draws the selected project's milestones. Charts shows the trends.
4. Example rows | Each sheet's first data row holds an example for the 'Pump Station Refurbishment (example)' project so you can see the expected format. Delete those rows' contents before real use.
Colour key
Blue text | Input cells - type here.
Grey cells / grey headers | Formulas - do not overwrite (Project Health, budgets, buckets, flags, ranks).
Yellow | Selector cells (Project Summary C3, Search B3).
Green / Amber / Red | Health ratings. Schedule and Budget: green below 95%, amber 95-115%, red above 115% (same rules as the web app). Risk: red if any open Critical risk, amber if any High.
How the numbers work (same rules as the web tool)
Effective budget | Latest Approved Budget if entered, otherwise Original Budget plus approved Variations.
Forecast at completion | For each project and month, an Actual replaces that month's Forecast - they are never added together. Enter one line per project, month and type.
Revised completion | Target Completion plus days from approved EOT Claims (Days Granted, or Days Claimed if none recorded).
Overdue project | Target Completion has passed and the status is not Project Completion, Defects Liability, Complete or Cancelled.
Risk score | Likelihood (1-5) x Consequence (1-5): 16+ Critical, 10-15 High, 5-9 Medium, below 5 Low.
Limits (fixed row capacity - extend by copying the last formula row down)
Projects | 100
Tasks | 1,000
Cash Flow | 2,000
Every other register | 500 rows each
Dashboard portfolio table | Shows the first 30 projects; the Projects sheet always shows all.
Macros (optional - see the VBA folder)
What they add | Global search across every sheet, an automatic Activity Log (who changed what, when), recurring tasks (marking a recurring task Done creates the next one), one-click PDF of the Project Summary, a dated backup copy, and an Outlook email digest of overdue / expiring items.
Without macros | Everything above that is a formula still works - dashboard, health, alerts, summary, Gantt, charts, dropdowns. Use Ctrl+F (Within: Workbook) for search.
Keeping the data in your company's OneDrive / SharePoint
Where to save | Save this file in a OneDrive for Business or SharePoint document library your IT department approves. The data then lives in the company tenant under its retention, backup and access policies.
Access control | Use the library's sharing settings: Edit for the project team, View for read-only stakeholders. Excel Version History restores earlier versions.
Co-authoring | Several people can edit the same .xlsx at once in Excel desktop or the browser. Avoid sorting a register while others are editing it.
What is not in a spreadsheet | Per-user logins and per-project permissions, file attachments, site photo upload/map, scheduled emails and the AI assistant. Link to files in SharePoint (link columns on Documents, Meeting Minutes and Site Visits) instead.
Sheet index
Dashboard | Portfolio table, alerts, today & upcoming, top risks.
Project Summary | One-page report for the selected project.
Gantt | Weekly bar chart of the selected project's milestones.
Charts | Status, budget vs forecast, S-curve, risk bands.
Search | Cross-sheet search (needs the macros).
Projects | One row per project. Grey columns are formulas - do not type in them.
Tasks | Register - one row per record.
Actions | Register - one row per record.
Risks | Register - one row per record.
RFIs | Register - one row per record.
Defects | Register - one row per record.
Variations | Register - one row per record.
EOT Claims | Register - one row per record.
Cash Flow | Register - one row per record.
Milestones | Register - one row per record.
Payment Claims | Register - one row per record.
Contracts | Register - one row per record.
Subcontractors | Register - one row per record.
Permits | Register - one row per record.
Insurance Warranties | Register - one row per record.
Stakeholders | Register - one row per record.
Meeting Minutes | Register - one row per record.
Correspondence | Register - one row per record.
Documents | Register - one row per record.
SQE Issues | Register - one row per record.
Safety Inspections | Register - one row per record.
Env Monitoring | Register - one row per record.
Site Visits | Register - one row per record.
Training Records | Register - one row per record.
Toolbox Talks | Register - one row per record.
Lessons Learned | Register - one row per record.
Enquiries | Register - one row per record.
Tenders | Register - one row per record.
Performance Reviews | Register - one row per record.
Checklist | Register - one row per record.
Activity Log | Written by the macro (ThisWorkbook module). Leave empty if macros are not installed.
Lists | Dropdown values. Edit here to change a list.
Calc | Chart working figures.

## Dashboard
APD Project Management Dashboard |  |  |  |  | As at | 2026-10-11
Every figure here is a live formula over the register sheets.
Total Projects |  | In Construction |  | Overdue Projects |  | Total Approved Budget
1 |  | 1 |  | 0 |  | 1060000
Portfolio (first 30 projects - full list on the Projects sheet)
Project | Status | Project Manager | Revised Completion | Effective Budget | Forecast at Completion | Budget Variance | Schedule | Budget | Risk | Overall | Open Tasks | Open Actions | Open RFIs | Open Defects
Pump Station Refurbishment (example) | Construction | J. Smith | 2026-12-15 | 1060000 | 1060000 | 0 | Green | Amber | Red | Red | 1 | 1 | 1 | 1
Alerts |  |  |  | Today & Upcoming
Alert | Count |  |  | Due | Tasks | Actions | Total
Projects past target completion | 0 |  |  | Overdue | 0 | 1 | 1
Projects with Red overall health | 1 |  |  | Due Today | 0 | 0 | 0
Overdue tasks | 0 |  |  | Due This Week | 1 | 0 | 1
Overdue actions / decisions | 1 |  |  | Later | 0 | 0 | 0
Overdue RFIs | 0 |  |  | No Due Date | 0 | 0 | 0
RFIs due within 7 days | 1
Overdue defects | 0
Overdue correspondence responses | 1
Overdue risk actions | 0
Overdue commissioning / handover items | 0
Permits expired or expiring (60 days) | 1
Insurance / warranties expired or expiring | 0
Subcontractor insurance expired or expiring | 1
Training records expired or expiring | 0
Environmental exceedances | 0
Open High / Critical SQE issues | 0
Payment claims awaiting certification | 0
Upcoming tasks (next 15 open, soonest first) |  |  |  |  | Upcoming actions & decisions (next 15 open)
Task | Project | Due | Bucket |  | Action | Project | Owner | Due | Bucket
Order replacement pump seals | Pump Station Refurbishment (example) | 2026-10-16 | Due This Week |  | Issue revised switchboard drawings | Pump Station Refurbishment (example) | M. Lee | 2026-10-09 | Overdue
Top open risks (highest inherent score first)
Risk | Project | Score | Band | Owner | Status | Due
Switchboard delivery delay | Pump Station Refurbishment (example) | 16 | Critical | J. Smith | Mitigating | 2026-10-25
Formulas:
Revised Completion = IF([Total Projects]="","",IFERROR(IF(INDEX(Projects!$W2:W101,MATCH([Total Projects],Projects!$A2:A101,0))="","",INDEX(Projects!$W2:W101,MATCH([Total Projects],Projects!$A2:A101,0))),""))
In Construction = IFERROR(IF(INDEX(Tasks!$E2:E1001,MATCH(SMALL(Tasks!$I2:I1001,ROWS(A64:[Total Projects])),Tasks!$I2:I1001,0))="","",INDEX(Tasks!$E2:E1001,MATCH(SMALL(Tasks!$I2:I1001,ROWS(A64:[Total Projects])),Tasks!$I2:I1001,0))),"")
Budget = IFERROR(IF(INDEX(Actions!$G2:G501,MATCH(SMALL(Actions!$N2:N501,ROWS(F64:[Forecast at Completion])),Actions!$N2:N501,0))="","",INDEX(Actions!$G2:G501,MATCH(SMALL(Actions!$N2:N501,ROWS(F64:[Forecast at Completion])),Actions!$N2:N501,0))),"")
Total Approved Budget = IFERROR(IF(INDEX(Risks!$L2:L501,MATCH(LARGE(Risks!$S2:S501,ROWS(A83:[Total Projects])),Risks!$S2:S501,0))="","",INDEX(Risks!$L2:L501,MATCH(LARGE(Risks!$S2:S501,ROWS(A83:[Total Projects])),Risks!$S2:S501,0))),"")

## Project Summary
Project Summary
Pick a project in C3. Print this sheet (or use the PDF macro) as a one-page project report.
| Project: | Pump Station Refurbishment (example)
| Overview |  |  | Health
| Status | Construction |  | Overall | Red
| Project Manager | J. Smith |  | Schedule | Green
| Project Director | A. Jones |  | Budget | Amber
| Project Sponsor | Operations |  | Risk | Red
| Location | Nathalia |  | Schedule: 70% of timeframe elapsed ¦ Budget: 100% of budget forecast ¦ Risk: 1 critical, 0 high open
| Contractor | ABC Civil Pty Ltd
| Budget |  |  | Schedule
| Original Budget | 1000000 |  | Start Date | 2026-05-14
| Latest Approved Budget | 1060000 |  | Target Completion | 2026-12-10
| Approved Variations | 60000 |  | Approved EOT days | 5
| Effective Budget | 1060000 |  | Revised Completion | 2026-12-15
| Expenditure to Date | 560000 |  | Actual Completion
| Forecast at Completion | 1060000 |  | Timeframe elapsed | 69.77%
| Variance (budget - forecast) | 0
| Forecast % of budget | 100% |  | Open items
|  |  |  | Open tasks | 1
|  |  |  | Open actions | 1
|  |  |  | Open RFIs | 1
|  |  |  | Open defects | 1
Milestones
| Activity | WBS | % Complete | Original | Forecast | Slip (days)
| Procure pumps and switchboard | 1.1 | 80 | 2026-10-01 | 2026-10-21 | 20
| Install and commission | 1.2 | 20 | 2026-11-30 | 2026-12-10 | 10
Top open risks
| Risk | Band | Owner | Status | Mitigation | Due
| Switchboard delivery delay | Critical | J. Smith | Mitigating | Expedite order; confirm factory slot | 2026-10-25
Variations
| Title | Reference | Cost Impact | Time (days) | Status | Date Raised
| Additional valve chamber | VO-01 | 60000 | 10 | Approved | 2026-09-01
Open actions & decisions
| Title | Type | Owner | Due | Status | Bucket
| Issue revised switchboard drawings | Action | M. Lee | 2026-10-09 | Open | Overdue
Formulas:
Original = IFERROR(IF(INDEX(Milestones!$F2:F501,MATCH(ROWS(B29:[Activity]),Milestones!$K2:K501,0))="","",INDEX(Milestones!$F2:F501,MATCH(ROWS(B29:[Activity]),Milestones!$K2:K501,0))),"")
Original = IFERROR(IF(INDEX(Actions!$G2:G501,MATCH(ROWS(B69:[Activity]),Actions!$O2:O501,0))="","",INDEX(Actions!$G2:G501,MATCH(ROWS(B69:[Activity]),Actions!$O2:O501,0))),"")
Forecast = IFERROR(IF(INDEX(Milestones!$G2:G501,MATCH(ROWS(B29:[Activity]),Milestones!$K2:K501,0))="","",INDEX(Milestones!$G2:G501,MATCH(ROWS(B29:[Activity]),Milestones!$K2:K501,0))),"")
Slip (days) = IFERROR(IF(INDEX(Risks!$L2:L501,MATCH(LARGE(Risks!$T2:T501,ROWS(B45:[Activity])),Risks!$T2:T501,0))="","",INDEX(Risks!$L2:L501,MATCH(LARGE(Risks!$T2:T501,ROWS(B45:[Activity])),Risks!$T2:T501,0))),"")
Slip (days) = IFERROR(IF(INDEX(Variations!$I2:I501,MATCH(ROWS(B57:[Activity]),Variations!$L2:L501,0))="","",INDEX(Variations!$I2:I501,MATCH(ROWS(B57:[Activity]),Variations!$L2:L501,0))),"")

## Gantt
Gantt - milestones for the project selected on 'Project Summary'
Blue = planned span (start to forecast completion); green = % complete. The red header marks the current week.
Project: | Pump Station Refurbishment (example)
WBS | Activity | Start | Finish | % | time axis 2026-06-08 to 2027-05-31
1.1 | Procure pumps and switchboard | 2026-06-13 | 2026-10-21 | 80
1.2 | Install and commission | 2026-09-11 | 2026-12-10 | 20

## Charts
Charts
Driven by the Dashboard portfolio table and the Calc sheet.

## Search
Global Search
Type a word in B3 and press Enter. Needs the macros (see VBA/README). Without them use Ctrl+F > Options > Within: Workbook.
Search for:
Sheet | Row key | Matching text | Go to

## Projects
Project Name | Description | Asset Type | Status | BP Ref No | Project Manager | Project Director | Project Sponsor | Location | Contractor | Contract Value | Original Budget | Latest Approved Budget | Start Date | Target Completion | Actual Completion | Approved Variations | Effective Budget | Expenditure to Date | Forecast at Completion | Budget Variance | Approved EOT Days | Revised Completion | Overdue | Schedule Elapsed % | Schedule Health | Forecast % of Budget | Budget Health | Critical Risks | High Risks | Risk Health | Overall Health | Open Tasks | Open Actions | Open RFIs | Open Defects | Health Notes
Pump Station Refurbishment (example) | Replace two pumps and switchboard at the Nathalia pump station | Pump Station | Construction | 3323 | J. Smith | A. Jones | Operations | Nathalia | ABC Civil Pty Ltd | 920000 | 1000000 | 1060000 | 2026-05-14 | 2026-12-10 |  | 60000 | 1060000 | 560000 | 1060000 | 0 | 5 | 2026-12-15 |  | 69.77% | Green | 100% | Amber | 1 | 0 | Red | Red | 1 | 1 | 1 | 1 | Schedule: 70% of timeframe elapsed ¦ Budget: 100% of budget forecast ¦ Risk: 1 critical, 0 high open
Formulas:
Revised Completion = IF([Project Name]="","",IF([Target Completion]="","",[Target Completion]+[Approved EOT Days]))
Overdue = IF([Project Name]="","",IF([Target Completion]="","",IF(AND(NOT(OR([Status]="Project Completion",[Status]="Defects Liability",[Status]="Complete",[Status]="Cancelled")),[Target Completion]<TODAY()),"Overdue","")))
Schedule Elapsed % = IF([Project Name]="","",IF(OR([Start Date]="",[Revised Completion]=""),"",IF([Revised Completion]<=[Start Date],"",(TODAY()-[Start Date])/([Revised Completion]-[Start Date]))))
Note on A1: Unique name. Registers pick the project from this list.
Note on K1: Display only (not part of health maths).
Note on M1: Leave blank if unchanged from the original.
Note on T1: Actual for months with an actual, otherwise forecast (no double counting).

## Tasks
Project | Title | Description | Status | Due Date | Recurrence | Completed Date | Bucket | Upcoming Rank
Pump Station Refurbishment (example) | Order replacement pump seals | Confirm lead time with supplier | In Progress | 2026-10-16 | None |  | Due This Week | 46311
Formulas:
Bucket = IF([Title]="","",IF(OR([Status]="Done"),"Done",IF([Due Date]="","No Due Date",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]=TODAY(),"Due Today",IF([Due Date]<TODAY()+7,"Due This Week","Later"))))))
Note on A1: Leave blank for a portfolio-wide task.
Note on F1: Marking a recurring task Done creates the next one (macro).

## Actions
Project | Type | Title | Description | Category | Owner | Due Date | Status | Date Raised | Date Closed | Meeting | Notes | Bucket | Upcoming Rank | Summary Seq
Pump Station Refurbishment (example) | Action | Issue revised switchboard drawings |  | Design | M. Lee | 2026-10-09 | Open | 2026-09-21 |  |  |  | Overdue | 46304 | 1
Formulas:
Bucket = IF([Title]="","",IF(OR([Status]="Done"),"Done",IF([Due Date]="","No Due Date",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]=TODAY(),"Due Today",IF([Due Date]<TODAY()+7,"Due This Week","Later"))))))
Note on K1: Optional: title of the meeting the action came from.

## Risks
Project | Type | Title | Description | Category | Inherent Likelihood | Inherent Consequence | Residual Likelihood | Residual Consequence | Mitigation | Owner | Due Date | Status | Inherent Score | Inherent Band | Residual Score | Residual Band | Overdue | Top Rank | Summary Rank
Pump Station Refurbishment (example) | Risk | Switchboard delivery delay |  | Programme | Likely | Major | Possible | Moderate | Expedite order; confirm factory slot | J. Smith | 2026-10-25 | Mitigating | 16 | Critical | 9 | Medium |  | 17 | 17
Formulas:
Overdue = IF(AND([Title]<>"",[Status]<>"Closed",[Due Date]<>"",[Due Date]<TODAY()),"Overdue","")

## RFIs
Project | RFI Number | Subject | Question | Response | Raised To | Status | Date Raised | Date Required | Date Answered | Notes | Flag
Pump Station Refurbishment (example) | RFI-001 | Pump base level | Confirm finished level of plinth |  | Design consultant | Open | 2026-10-05 | 2026-10-14 |  |  | Due Soon
Formulas:
Flag = IF(OR([RFI Number]="",[Status]<>"Open",[Date Required]=""),"",IF([Date Required]<TODAY(),"Overdue",IF([Date Required]<=TODAY()+7,"Due Soon","")))

## Defects
Project | Title | Description | Location | Category | Assigned To | Due Date | Status | Date Raised | Date Closed | Retention Held | Notes | Flag
Pump Station Refurbishment (example) | Chipped paint on pump housing |  | Pump 2 | Finishes | ABC Civil | 2026-10-21 | Open | 2026-10-08 |  | 2500
Formulas:
Flag = IF(OR([Title]="",[Status]<>"Open",[Due Date]=""),"",IF([Due Date]<TODAY(),"Overdue",""))

## Variations
Project | Reference | Title | Description | Category | Cost Impact | Time Impact Days | Status | Date Raised | Date Decided | Notes | Summary Seq
Pump Station Refurbishment (example) | VO-01 | Additional valve chamber |  | Scope | 60000 | 10 | Approved | 2026-09-01 | 2026-09-11 |  | 1

## EOT Claims
Project | Reference | Title | Cause | Description | Days Claimed | Days Granted | Status | Date Submitted | Date Decided | Notes | Days Counted
Pump Station Refurbishment (example) | EOT-01 | Wet weather delay | Weather |  | 8 | 5 | Approved | 2026-09-16 | 2026-09-26 |  | 5
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Cash Flow
Project | Month | Type | Amount | Month Key | Counted Amount
Pump Station Refurbishment (example) | 2026-08-12 | Actual | 250000 | 2026-08-01 | 250000
Pump Station Refurbishment (example) | 2026-09-11 | Actual | 310000 | 2026-09-01 | 310000
Pump Station Refurbishment (example) | 2026-10-11 | Forecast | 280000 | 2026-10-01 | 280000
Pump Station Refurbishment (example) | 2026-11-10 | Forecast | 220000 | 2026-11-01 | 220000
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Month Key = IF(OR([Project]="",[Month]=""),"",DATE(YEAR([Month]),MONTH([Month]),1))
Note on B1: Any date in the month; it is normalised to the 1st.
Note on F1: An Actual replaces that month's Forecast so nothing is double counted.

## Milestones
Project | WBS Item | Task / Activity | % Complete | Start Date | Original Completion | Forecast Completion | Actual Completion | Notes | Slip (days) | Summary Seq
Pump Station Refurbishment (example) | 1.1 | Procure pumps and switchboard | 80 | 2026-06-13 | 2026-10-01 | 2026-10-21 |  |  | 20 | 1
Pump Station Refurbishment (example) | 1.2 | Install and commission | 20 | 2026-09-11 | 2026-11-30 | 2026-12-10 |  |  | 10 | 2

## Payment Claims
Project | Contract | Claim Number | Period Ending | Claimed Amount | Certified Amount | Status | Date Submitted | Date Certified | Date Paid | Notes
Pump Station Refurbishment (example) | ABC Civil Pty Ltd | PC-01 | 2026-09-10 | 250000 | 245000 | Paid | 2026-09-13 | 2026-09-21 | 2026-10-03
Note on B1: Party name of the contract this claim is against (optional).

## Contracts
Project | Party Type | Party Name | Discipline / Scope | Contract Number | Contract Form | Contract Value | Contingency | PO Value | Provisional Items | Retention % | DLP Months | Execution Date | Start Date | Completion Date | Status | Notes | Claimed to Date | Remaining
Pump Station Refurbishment (example) | Contractor | ABC Civil Pty Ltd | Construction | C-1042 | AS4000-1997 | 920000 | 46000 |  |  | 5 | 12 | 2026-04-24 | 2026-05-14 | 2026-12-10 | Active |  | 250000 | 670000

## Subcontractors
Project | Company Name | Trade | Contact Name | Contact Details | Contract Value | Start Date | End Date | Status | Insurance Expiry | Notes | Insurance Flag
Pump Station Refurbishment (example) | Sparky Electrical | Electrical | T. Nguyen | 0400 000 000 | 85000 | 2026-09-01 | 2026-11-20 | Active | 2026-11-10 |  | Expiring Soon
Formulas:
Insurance Flag = IF(OR([Company Name]="",OR([Status]="Completed",[Status]="Terminated")),"",IF([Insurance Expiry]="","",IF([Insurance Expiry]<TODAY(),"Expired",IF([Insurance Expiry]<=TODAY()+60,"Expiring Soon","OK"))))

## Permits
Project | Title | Category | Reference Number | Issuing Authority | Status | Date Applied | Date Approved | Expiry Date | Notes | Expiry Flag
Pump Station Refurbishment (example) | Works within waterway permit | Environmental | WW-4471 | Catchment Authority | Approved | 2026-07-13 | 2026-08-12 | 2026-11-25 |  | Expiring Soon
Formulas:
Expiry Flag = IF([Title]="","",IF([Expiry Date]="","",IF([Expiry Date]<TODAY(),"Expired",IF([Expiry Date]<=TODAY()+60,"Expiring Soon","OK"))))

## Insurance Warranties
Project | Type | Title | Provider | Reference Number | Coverage Details | Start Date | Expiry Date | Notes | Expiry Flag
Pump Station Refurbishment (example) | Insurance | Public liability | Insurer Co | PL-99120 |  | 2026-04-24 | 2027-04-19 |  | OK
Formulas:
Expiry Flag = IF([Title]="","",IF([Expiry Date]="","",IF([Expiry Date]<TODAY(),"Expired",IF([Expiry Date]<=TODAY()+60,"Expiring Soon","OK"))))

## Stakeholders
Project | Name | Organization | Role | Email | Phone | Notes
Pump Station Refurbishment (example) | Pat Citizen | Local council | Approvals officer | pat@example.com | 0400 111 222

## Meeting Minutes
Project | Title | Meeting Date | Meeting Type | Location | Attendees | Summary | Next Meeting | Notes | Document Link
Pump Station Refurbishment (example) | Fortnightly progress meeting | 2026-10-07 | Progress | Site office | J. Smith, M. Lee, ABC Civil | Pumps on order; switchboard slipped 10 days | 2026-10-21
Note on J1: Paste a OneDrive/SharePoint link to the minutes file.

## Correspondence
Project | Reference | Direction | Correspondent | Subject | Summary | Date Sent | Response Due | Status | Date Closed | Notes | Flag
Pump Station Refurbishment (example) | COR-01 | Incoming | ABC Civil | Notice of delay - switchboard |  | 2026-10-02 | 2026-10-10 | Open |  |  | Overdue
Formulas:
Flag = IF(OR([Subject]="",[Status]<>"Open",[Response Due]=""),"",IF([Response Due]<TODAY(),"Overdue",""))

## Documents
Project | Document Number | Title | Category | Revision | Status | Issue Date | Description | Notes | File Link
Pump Station Refurbishment (example) | PS-DWG-001 | General arrangement | Drawing | B | Approved | 2026-08-27
Note on J1: OneDrive/SharePoint link to the document.

## SQE Issues
Project | Category | Severity | Title | Description | Corrective Action | Date Occurred | Status | Date Closed | Reported By
Pump Station Refurbishment (example) | Safety | Medium | Near miss - excavator swing radius |  | Exclusion zone barriers installed | 2026-09-29 | In Progress |  | M. Lee

## Safety Inspections
Project | Inspection Date | Inspection Type | Location | Conducted By | Score | Findings | Corrective Action | Status | Date Closed | Notes
Pump Station Refurbishment (example) | 2026-10-04 | Weekly site inspection | Site | M. Lee | 92 | Housekeeping around laydown area |  | Open

## Env Monitoring
Project | Parameter | Location | Monitoring Date | Reading | Unit | Limit | Limit Type | Corrective Action | Notes | Result
Pump Station Refurbishment (example) | Turbidity | Downstream of works | 2026-10-06 | 18 | NTU | 25 | Max |  |  | OK

## Site Visits
Project | Visit Date | Location | Visited By | Notes | Discussion Notes | Photos Link
Pump Station Refurbishment (example) | 2026-10-08 | Pump station site | J. Smith | Footings complete, pumps on site next week
Note on G1: Link to the OneDrive/SharePoint folder of photos for this visit.

## Training Records
Project | Person Name | Company | Training Type | Completion Date | Expiry Date | Certificate Number | Notes | Expiry Flag
Pump Station Refurbishment (example) | T. Nguyen | Sparky Electrical | Confined space entry | 2025-12-15 | 2026-12-15 | CS-7781 |  | OK
Formulas:
Expiry Flag = IF([Person Name]="","",IF([Expiry Date]="","",IF([Expiry Date]<TODAY(),"Expired",IF([Expiry Date]<=TODAY()+60,"Expiring Soon","OK"))))

## Toolbox Talks
Project | Talk Date | Topic | Conducted By | Attendees | Key Points | Notes
Pump Station Refurbishment (example) | 2026-10-09 | Working near live electrical | M. Lee | Site crew (6) | Isolation and lock-out procedure

## Lessons Learned
Project | Type | Title | Category | Description | Recommendation
Pump Station Refurbishment (example) | Negative | Long-lead switchboard ordered late | Procurement | Order placed after design freeze | Order long-lead items at 60% design

## Enquiries
Project | Reference | Category | Source | Contact Name | Contact Details | Description | Date Received | Status | Assigned To | Resolution | Date Resolved | Notes
Pump Station Refurbishment (example) | ENQ-01 | Noise | Phone | Resident, Main St |  | Early morning pump testing noise | 2026-10-05 | In Progress | J. Smith

## Tenders
Project | Package Number | Title | Description | Method | Status | Date Issued | Closing Date | Submissions | Estimated Value | Awarded To | Awarded Value | Date Awarded | Notes
Pump Station Refurbishment (example) | T-2201 | Electrical works package |  | Selective | Awarded | 2026-06-13 | 2026-07-03 | 4 | 90000 | Sparky Electrical | 85000 | 2026-07-13

## Performance Reviews
Project | Reviewee Name | Review Period | Review Date | Quality | Safety | Timeliness | Communication | Comments | Overall (1-5) | Band
Pump Station Refurbishment (example) | ABC Civil Pty Ltd | Q3 | 2026-10-01 | 4 | 4 | 3 | 5 | Good workmanship; programme slipping | 4 | Good

## Checklist
Project | Phase | Title | Description | Responsible | Due Date | Completed Date | Status | Notes | Flag
Pump Station Refurbishment (example) | Commissioning | Pump performance test |  | ABC Civil | 2026-11-25 |  | Not Started
Formulas:
Flag = IF(OR([Title]="",[Status]="Complete",[Status]="Not Applicable",[Due Date]=""),"",IF([Due Date]<TODAY(),"Overdue",""))

## Activity Log
Timestamp | User | Sheet | Cell | Old Value | New Value

## Lists
ProjectStatus | TaskStatus | Recurrence | CashType | VariationStatus | RiskType | Likelihood | Consequence | RiskStatus | ActionType | ActionStatus | PermitStatus | LessonType | SqeCategory | SqeSeverity | SqeStatus | EotStatus | ChecklistPhase | ChecklistStatus | DefectStatus | PaymentStatus | IWType | RfiStatus | DocStatus | EnquiryCategory | EnquiryStatus | SubStatus | PartyType | ContractStatus | Direction | CorrStatus | LimitType | SafetyInspStatus | TenderMethod | TenderStatus | Rating
Planning | To Do | None | Actual | Proposed | Risk | Rare | Insignificant | Open | Action | Open | Pending | Positive | Safety | Low | Open | Submitted | Commissioning | Not Started | Open | Submitted | Insurance | Open | Draft | Noise | Open | Engaged | Consultant | Active | Incoming | Open | Max | Open | Open | Planned | 1
Design | In Progress | Daily | Forecast | Approved | Opportunity | Unlikely | Minor | Mitigating | Decision | In Progress | Approved | Negative | Quality | Medium | In Progress | Approved | Handover | In Progress | Rectified | Certified | Warranty | Answered | For Review | Traffic | In Progress | Active | Contractor | Complete | Outgoing | Closed | Min | In Progress | Selective | Issued | 2
Tender | Done | Weekly |  | Rejected |  | Possible | Moderate | Closed |  | Done | Rejected |  | Environment | High | Closed | Rejected |  | Complete | Verified | Disputed |  | Closed | Approved | Dust | Resolved | Completed |  | Terminated |  |  |  | Closed | Direct Engage | Evaluation | 3
Construction |  | Monthly |  |  |  | Likely | Major | [6 empty] | Critical |  |  |  | Not Applicable | Disputed | Paid |  |  | Superseded | Access | Closed | Terminated | [6 empty] | Expression of Interest | Awarded | 4
Project Completion | [5 empty] | Almost Certain | Severe | [16 empty] | Other | [9 empty] | Cancelled | 5
Defects Liability
Complete
On Hold
Cancelled

## Calc
Working figures for the Charts sheet - do not edit.
Status | Projects | Month | Spend in month | Cumulative | Approved budget | Open risk band | Count
Planning | 0 | 2026-08-01 | 250000 | 250000 | 1060000 | Critical | 1
Design | 0 | 2026-09-01 | 310000 | 560000 | 1060000 | High | 0
Tender | 0 | 2026-10-01 | 280000 | 840000 | 1060000 | Medium | 0
Construction | 1 | 2026-11-01 | 220000 | 1060000 | 1060000 | Low | 0
Project Completion | 0 | 2026-12-01 | 0 | 1060000 | 1060000
Defects Liability | 0 | 2027-01-01 | 0 | 1060000 | 1060000
Complete | 0 | 2027-02-01 | 0 | 1060000 | 1060000
On Hold | 0 | 2027-03-01 | 0 | 1060000 | 1060000
Cancelled | 0 | 2027-04-01 | 0 | 1060000 | 1060000
|  | 2027-05-01 | 0 | 1060000 | 1060000
|  | 2027-06-01 | 0 | 1060000 | 1060000
|  | 2027-07-01 | 0 | 1060000 | 1060000
|  | 2027-08-01 | 0 | 1060000 | 1060000
|  | 2027-09-01 | 0 | 1060000 | 1060000
|  | 2027-10-01 | 0 | 1060000 | 1060000
|  | 2027-11-01 | 0 | 1060000 | 1060000
|  | 2027-12-01 | 0 | 1060000 | 1060000
|  | 2028-01-01 | 0 | 1060000 | 1060000
|  | 2028-02-01 | 0 | 1060000 | 1060000
|  | 2028-03-01 | 0 | 1060000 | 1060000
|  | 2028-04-01 | 0 | 1060000 | 1060000
|  | 2028-05-01 | 0 | 1060000 | 1060000
|  | 2028-06-01 | 0 | 1060000 | 1060000
|  | 2028-07-01 | 0 | 1060000 | 1060000
Formulas:
Month = EDATE([Month, row above],1)