## Guide
APD Project Tracker
A single-file, OneDrive/SharePoint-hosted version of the APD Project Management Dashboard (without the AI features).
Getting started
1. Add a project | Go to Projects and type the project name in the first empty row (column A). Everything else on that row is optional; grey columns calculate themselves.
2. Log records | On any register sheet, pick the Project from the dropdown in column A and fill in the row. Dropdowns, date and number checks are built in.
3. View results | Dashboard shows the portfolio, alerts and upcoming work. Project Summary (pick a project in C3) is a printable one-page report. Gantt draws the selected project's milestones. Charts shows the trends.
4. Example rows | This is the blank copy: every sheet is empty and ready for your data.
Colour key
Blue text | Input cells - type here.
Grey cells / grey headers | Formulas - do not overwrite (Project Health, budgets, buckets, flags, ranks).
Yellow | Selector cells (Project Summary C3, Search B3).
Green / Amber / Red | Health ratings. Schedule and Budget: green below 95%, amber 95-115%, red above 115% (same rules as the web app). Risk: red if any open Critical risk, amber if any High.
How the numbers work (same rules as the web tool)
Effective budget | Latest Approved Budget if entered, otherwise Original Budget plus approved Variations.
Forecast at completion | For each project and month, an Actual replaces that month's Forecast - they are never added together. Enter one line per project, month and type.
Revised completion | Target Completion plus days from approved EOT Claims (Days Granted, or Days Claimed if none recorded).
Overdue project | Target Completion has passed and the status is not Project Completion, Defects Liability, Complete or Cancelled.
Risk score | Likelihood (1-5) x Consequence (1-5): 16+ Critical, 10-15 High, 5-9 Medium, below 5 Low.
Limits (fixed row capacity - extend by copying the last formula row down)
Projects | 100
Tasks | 1,000
Cash Flow | 2,000
Every other register | 500 rows each
Dashboard portfolio table | Shows the first 30 projects; the Projects sheet always shows all.
Macros (optional - see the VBA folder)
What they add | Global search across every sheet, an automatic Activity Log (who changed what, when), recurring tasks (marking a recurring task Done creates the next one), one-click PDF of the Project Summary, a dated backup copy, and an Outlook email digest of overdue / expiring items.
Without macros | Everything above that is a formula still works - dashboard, health, alerts, summary, Gantt, charts, dropdowns. Use Ctrl+F (Within: Workbook) for search.
Keeping the data in your company's OneDrive / SharePoint
Where to save | Save this file in a OneDrive for Business or SharePoint document library your IT department approves. The data then lives in the company tenant under its retention, backup and access policies.
Access control | Use the library's sharing settings: Edit for the project team, View for read-only stakeholders. Excel Version History restores earlier versions.
Co-authoring | Several people can edit the same .xlsx at once in Excel desktop or the browser. Avoid sorting a register while others are editing it.
What is not in a spreadsheet | Per-user logins and per-project permissions, file attachments, site photo upload/map, scheduled emails and the AI assistant. Link to files in SharePoint (link columns on Documents, Meeting Minutes and Site Visits) instead.
Sheet index
Dashboard | Portfolio table, alerts, today & upcoming, top risks.
Project Summary | One-page report for the selected project.
Gantt | Weekly bar chart of the selected project's milestones.
Charts | Status, budget vs forecast, S-curve, risk bands.
Search | Cross-sheet search (needs the macros).
Projects | One row per project. Grey columns are formulas - do not type in them.
Tasks | Register - one row per record.
Actions | Register - one row per record.
Risks | Register - one row per record.
RFIs | Register - one row per record.
Defects | Register - one row per record.
Variations | Register - one row per record.
EOT Claims | Register - one row per record.
Cash Flow | Register - one row per record.
Milestones | Register - one row per record.
Payment Claims | Register - one row per record.
Contracts | Register - one row per record.
Subcontractors | Register - one row per record.
Permits | Register - one row per record.
Insurance Warranties | Register - one row per record.
Stakeholders | Register - one row per record.
Meeting Minutes | Register - one row per record.
Correspondence | Register - one row per record.
Documents | Register - one row per record.
SQE Issues | Register - one row per record.
Safety Inspections | Register - one row per record.
Env Monitoring | Register - one row per record.
Site Visits | Register - one row per record.
Training Records | Register - one row per record.
Toolbox Talks | Register - one row per record.
Lessons Learned | Register - one row per record.
Enquiries | Register - one row per record.
Tenders | Register - one row per record.
Performance Reviews | Register - one row per record.
Checklist | Register - one row per record.
Activity Log | Written by the macro (ThisWorkbook module). Leave empty if macros are not installed.
Lists | Dropdown values. Edit here to change a list.
Calc | Chart working figures.

## Dashboard
APD Project Management Dashboard |  |  |  |  | As at | 2026-10-11
Every figure here is a live formula over the register sheets.
Total Projects |  | In Construction |  | Overdue Projects |  | Total Approved Budget
0 |  | 0 |  | 0 |  | 0
Portfolio (first 30 projects - full list on the Projects sheet)
Project | Status | Project Manager | Revised Completion | Effective Budget | Forecast at Completion | Budget Variance | Schedule | Budget | Risk | Overall | Open Tasks | Open Actions | Open RFIs | Open Defects
Alerts |  |  |  | Today & Upcoming
Alert | Count |  |  | Due | Tasks | Actions | Total
Projects past target completion | 0 |  |  | Overdue | 0 | 0 | 0
Projects with Red overall health | 0 |  |  | Due Today | 0 | 0 | 0
Overdue tasks | 0 |  |  | Due This Week | 0 | 0 | 0
Overdue actions / decisions | 0 |  |  | Later | 0 | 0 | 0
Overdue RFIs | 0 |  |  | No Due Date | 0 | 0 | 0
RFIs due within 7 days | 0
Overdue defects | 0
Overdue correspondence responses | 0
Overdue risk actions | 0
Overdue commissioning / handover items | 0
Permits expired or expiring (60 days) | 0
Insurance / warranties expired or expiring | 0
Subcontractor insurance expired or expiring | 0
Training records expired or expiring | 0
Environmental exceedances | 0
Open High / Critical SQE issues | 0
Payment claims awaiting certification | 0
Upcoming tasks (next 15 open, soonest first) |  |  |  |  | Upcoming actions & decisions (next 15 open)
Task | Project | Due | Bucket |  | Action | Project | Owner | Due | Bucket
Top open risks (highest inherent score first)
Risk | Project | Score | Band | Owner | Status | Due

## Project Summary
Project Summary
Pick a project in C3. Print this sheet (or use the PDF macro) as a one-page project report.
Project:
| Overview |  |  | Health
| Status |  |  | Overall
| Project Manager |  |  | Schedule
| Project Director |  |  | Budget
| Project Sponsor |  |  | Risk
Location
Contractor
| Budget |  |  | Schedule
| Original Budget |  |  | Start Date
| Latest Approved Budget |  |  | Target Completion
| Approved Variations |  |  | Approved EOT days
| Effective Budget |  |  | Revised Completion
| Expenditure to Date |  |  | Actual Completion
| Forecast at Completion |  |  | Timeframe elapsed
Variance (budget - forecast)
| Forecast % of budget |  |  | Open items
Open tasks
Open actions
Open RFIs
Open defects
Milestones
| Activity | WBS | % Complete | Original | Forecast | Slip (days)
Top open risks
| Risk | Band | Owner | Status | Mitigation | Due
Variations
| Title | Reference | Cost Impact | Time (days) | Status | Date Raised
Open actions & decisions
| Title | Type | Owner | Due | Status | Bucket

## Gantt
Gantt - milestones for the project selected on 'Project Summary'
Blue = planned span (start to forecast completion); green = % complete. The red header marks the current week.
Project: | 0
WBS | Activity | Start | Finish | % | time axis 2026-10-05 to 2027-09-27

## Charts
Charts
Driven by the Dashboard portfolio table and the Calc sheet.

## Search
Global Search
Type a word in B3 and press Enter. Needs the macros (see VBA/README). Without them use Ctrl+F > Options > Within: Workbook.
Search for:
Sheet | Row key | Matching text | Go to

## Projects
Project Name | Description | Asset Type | Status | BP Ref No | Project Manager | Project Director | Project Sponsor | Location | Contractor | Contract Value | Original Budget | Latest Approved Budget | Start Date | Target Completion | Actual Completion | Approved Variations | Effective Budget | Expenditure to Date | Forecast at Completion | Budget Variance | Approved EOT Days | Revised Completion | Overdue | Schedule Elapsed % | Schedule Health | Forecast % of Budget | Budget Health | Critical Risks | High Risks | Risk Health | Overall Health | Open Tasks | Open Actions | Open RFIs | Open Defects | Health Notes
Formulas:
Overdue = IF([Project Name]="","",IF([Target Completion]="","",IF(AND(NOT(OR([Status]="Project Completion",[Status]="Defects Liability",[Status]="Complete",[Status]="Cancelled")),[Target Completion]<TODAY()),"Overdue","")))
Schedule Elapsed % = IF([Project Name]="","",IF(OR([Start Date]="",[Revised Completion]=""),"",IF([Revised Completion]<=[Start Date],"",(TODAY()-[Start Date])/([Revised Completion]-[Start Date]))))
Note on A1: Unique name. Registers pick the project from this list.
Note on K1: Display only (not part of health maths).
Note on M1: Leave blank if unchanged from the original.
Note on T1: Actual for months with an actual, otherwise forecast (no double counting).

## Tasks
Project | Title | Description | Status | Due Date | Recurrence | Completed Date | Bucket | Upcoming Rank
Formulas:
Bucket = IF([Title]="","",IF(OR([Status]="Done"),"Done",IF([Due Date]="","No Due Date",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]=TODAY(),"Due Today",IF([Due Date]<TODAY()+7,"Due This Week","Later"))))))
Note on A1: Leave blank for a portfolio-wide task.
Note on F1: Marking a recurring task Done creates the next one (macro).

## Actions
Project | Type | Title | Description | Category | Owner | Due Date | Status | Date Raised | Date Closed | Meeting | Notes | Bucket | Upcoming Rank | Summary Seq
Formulas:
Bucket = IF([Title]="","",IF(OR([Status]="Done"),"Done",IF([Due Date]="","No Due Date",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]=TODAY(),"Due Today",IF([Due Date]<TODAY()+7,"Due This Week","Later"))))))
Note on K1: Optional: title of the meeting the action came from.

## Risks
Project | Type | Title | Description | Category | Inherent Likelihood | Inherent Consequence | Residual Likelihood | Residual Consequence | Mitigation | Owner | Due Date | Status | Inherent Score | Inherent Band | Residual Score | Residual Band | Overdue | Top Rank | Summary Rank
Formulas:
Overdue = IF(AND([Title]<>"",[Status]<>"Closed",[Due Date]<>"",[Due Date]<TODAY()),"Overdue","")

## RFIs
Project | RFI Number | Subject | Question | Response | Raised To | Status | Date Raised | Date Required | Date Answered | Notes | Flag
Formulas:
Flag = IF(OR([RFI Number]="",[Status]<>"Open",[Date Required]=""),"",IF([Date Required]<TODAY(),"Overdue",IF([Date Required]<=TODAY()+7,"Due Soon","")))

## Defects
Project | Title | Description | Location | Category | Assigned To | Due Date | Status | Date Raised | Date Closed | Retention Held | Notes | Flag
Formulas:
Flag = IF(OR([Title]="",[Status]<>"Open",[Due Date]=""),"",IF([Due Date]<TODAY(),"Overdue",""))

## Variations
Project | Reference | Title | Description | Category | Cost Impact | Time Impact Days | Status | Date Raised | Date Decided | Notes | Summary Seq

## EOT Claims
Project | Reference | Title | Cause | Description | Days Claimed | Days Granted | Status | Date Submitted | Date Decided | Notes | Days Counted
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Cash Flow
Project | Month | Type | Amount | Month Key | Counted Amount
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on B1: Any date in the month; it is normalised to the 1st.
Note on F1: An Actual replaces that month's Forecast so nothing is double counted.

## Milestones
Project | WBS Item | Task / Activity | % Complete | Start Date | Original Completion | Forecast Completion | Actual Completion | Notes | Slip (days) | Summary Seq

## Payment Claims
Project | Contract | Claim Number | Period Ending | Claimed Amount | Certified Amount | Status | Date Submitted | Date Certified | Date Paid | Notes
Note on B1: Party name of the contract this claim is against (optional).

## Contracts
Project | Party Type | Party Name | Discipline / Scope | Contract Number | Contract Form | Contract Value | Contingency | PO Value | Provisional Items | Retention % | DLP Months | Execution Date | Start Date | Completion Date | Status | Notes | Claimed to Date | Remaining

## Subcontractors
Project | Company Name | Trade | Contact Name | Contact Details | Contract Value | Start Date | End Date | Status | Insurance Expiry | Notes | Insurance Flag
Formulas:
Insurance Flag = IF(OR([Company Name]="",OR([Status]="Completed",[Status]="Terminated")),"",IF([Insurance Expiry]="","",IF([Insurance Expiry]<TODAY(),"Expired",IF([Insurance Expiry]<=TODAY()+60,"Expiring Soon","OK"))))

## Permits
Project | Title | Category | Reference Number | Issuing Authority | Status | Date Applied | Date Approved | Expiry Date | Notes | Expiry Flag
Formulas:
Expiry Flag = IF([Title]="","",IF([Expiry Date]="","",IF([Expiry Date]<TODAY(),"Expired",IF([Expiry Date]<=TODAY()+60,"Expiring Soon","OK"))))

## Insurance Warranties
Project | Type | Title | Provider | Reference Number | Coverage Details | Start Date | Expiry Date | Notes | Expiry Flag
Formulas:
Expiry Flag = IF([Title]="","",IF([Expiry Date]="","",IF([Expiry Date]<TODAY(),"Expired",IF([Expiry Date]<=TODAY()+60,"Expiring Soon","OK"))))

## Stakeholders
Project | Name | Organization | Role | Email | Phone | Notes

## Meeting Minutes
Project | Title | Meeting Date | Meeting Type | Location | Attendees | Summary | Next Meeting | Notes | Document Link
Note on J1: Paste a OneDrive/SharePoint link to the minutes file.

## Correspondence
Project | Reference | Direction | Correspondent | Subject | Summary | Date Sent | Response Due | Status | Date Closed | Notes | Flag
Formulas:
Flag = IF(OR([Subject]="",[Status]<>"Open",[Response Due]=""),"",IF([Response Due]<TODAY(),"Overdue",""))

## Documents
Project | Document Number | Title | Category | Revision | Status | Issue Date | Description | Notes | File Link
Note on J1: OneDrive/SharePoint link to the document.

## SQE Issues
Project | Category | Severity | Title | Description | Corrective Action | Date Occurred | Status | Date Closed | Reported By

## Safety Inspections
Project | Inspection Date | Inspection Type | Location | Conducted By | Score | Findings | Corrective Action | Status | Date Closed | Notes

## Env Monitoring
Project | Parameter | Location | Monitoring Date | Reading | Unit | Limit | Limit Type | Corrective Action | Notes | Result

## Site Visits
Project | Visit Date | Location | Visited By | Notes | Discussion Notes | Photos Link
Note on G1: Link to the OneDrive/SharePoint folder of photos for this visit.

## Training Records
Project | Person Name | Company | Training Type | Completion Date | Expiry Date | Certificate Number | Notes | Expiry Flag
Formulas:
Expiry Flag = IF([Person Name]="","",IF([Expiry Date]="","",IF([Expiry Date]<TODAY(),"Expired",IF([Expiry Date]<=TODAY()+60,"Expiring Soon","OK"))))

## Toolbox Talks
Project | Talk Date | Topic | Conducted By | Attendees | Key Points | Notes

## Lessons Learned
Project | Type | Title | Category | Description | Recommendation

## Enquiries
Project | Reference | Category | Source | Contact Name | Contact Details | Description | Date Received | Status | Assigned To | Resolution | Date Resolved | Notes

## Tenders
Project | Package Number | Title | Description | Method | Status | Date Issued | Closing Date | Submissions | Estimated Value | Awarded To | Awarded Value | Date Awarded | Notes

## Performance Reviews
Project | Reviewee Name | Review Period | Review Date | Quality | Safety | Timeliness | Communication | Comments | Overall (1-5) | Band

## Checklist
Project | Phase | Title | Description | Responsible | Due Date | Completed Date | Status | Notes | Flag
Formulas:
Flag = IF(OR([Title]="",[Status]="Complete",[Status]="Not Applicable",[Due Date]=""),"",IF([Due Date]<TODAY(),"Overdue",""))

## Activity Log
Timestamp | User | Sheet | Cell | Old Value | New Value

## Lists
ProjectStatus | TaskStatus | Recurrence | CashType | VariationStatus | RiskType | Likelihood | Consequence | RiskStatus | ActionType | ActionStatus | PermitStatus | LessonType | SqeCategory | SqeSeverity | SqeStatus | EotStatus | ChecklistPhase | ChecklistStatus | DefectStatus | PaymentStatus | IWType | RfiStatus | DocStatus | EnquiryCategory | EnquiryStatus | SubStatus | PartyType | ContractStatus | Direction | CorrStatus | LimitType | SafetyInspStatus | TenderMethod | TenderStatus | Rating
Planning | To Do | None | Actual | Proposed | Risk | Rare | Insignificant | Open | Action | Open | Pending | Positive | Safety | Low | Open | Submitted | Commissioning | Not Started | Open | Submitted | Insurance | Open | Draft | Noise | Open | Engaged | Consultant | Active | Incoming | Open | Max | Open | Open | Planned | 1
Design | In Progress | Daily | Forecast | Approved | Opportunity | Unlikely | Minor | Mitigating | Decision | In Progress | Approved | Negative | Quality | Medium | In Progress | Approved | Handover | In Progress | Rectified | Certified | Warranty | Answered | For Review | Traffic | In Progress | Active | Contractor | Complete | Outgoing | Closed | Min | In Progress | Selective | Issued | 2
Tender | Done | Weekly |  | Rejected |  | Possible | Moderate | Closed |  | Done | Rejected |  | Environment | High | Closed | Rejected |  | Complete | Verified | Disputed |  | Closed | Approved | Dust | Resolved | Completed |  | Terminated |  |  |  | Closed | Direct Engage | Evaluation | 3
Construction |  | Monthly |  |  |  | Likely | Major | [6 empty] | Critical |  |  |  | Not Applicable | Disputed | Paid |  |  | Superseded | Access | Closed | Terminated | [6 empty] | Expression of Interest | Awarded | 4
Project Completion | [5 empty] | Almost Certain | Severe | [16 empty] | Other | [9 empty] | Cancelled | 5
Defects Liability
Complete
On Hold
Cancelled

## Calc
Working figures for the Charts sheet - do not edit.
Status | Projects | Month | Spend in month | Cumulative | Approved budget | Open risk band | Count
Planning | 0 | 2026-10-01 | 0 | 0 | 0 | Critical | 0
Design | 0 | 2026-11-01 | 0 | 0 | 0 | High | 0
Tender | 0 | 2026-12-01 | 0 | 0 | 0 | Medium | 0
Construction | 0 | 2027-01-01 | 0 | 0 | 0 | Low | 0
Project Completion | 0 | 2027-02-01 | 0 | 0 | 0
Defects Liability | 0 | 2027-03-01 | 0 | 0 | 0
Complete | 0 | 2027-04-01 | 0 | 0 | 0
On Hold | 0 | 2027-05-01 | 0 | 0 | 0
Cancelled | 0 | 2027-06-01 | 0 | 0 | 0
|  | 2027-07-01 | 0 | 0 | 0
|  | 2027-08-01 | 0 | 0 | 0
|  | 2027-09-01 | 0 | 0 | 0
|  | 2027-10-01 | 0 | 0 | 0
|  | 2027-11-01 | 0 | 0 | 0
|  | 2027-12-01 | 0 | 0 | 0
|  | 2028-01-01 | 0 | 0 | 0
|  | 2028-02-01 | 0 | 0 | 0
|  | 2028-03-01 | 0 | 0 | 0
|  | 2028-04-01 | 0 | 0 | 0
|  | 2028-05-01 | 0 | 0 | 0
|  | 2028-06-01 | 0 | 0 | 0
|  | 2028-07-01 | 0 | 0 | 0
|  | 2028-08-01 | 0 | 0 | 0
|  | 2028-09-01 | 0 | 0 | 0
Formulas:
Month = EDATE([Month, row above],1)